## Start Here
ZSuite Partner Questionnaire
Welcome! It's great to have you as a partner! To begin implementation, we need a few things from your FI to get started.
|  | Name | Email | Phone Number
Executive Sponsor:
Primary Contact (Sales):
Primary Contact (Ongoing Support):
Post-Launch ZS Product Owner:
Compliance questions should be directed to:
Marketing/Branding questions should be directed to:
Invoices & Billing questions/related items should be directed to:
Who should receive ZEscrow notifications via email in the event we do not receive the expected daily files?
Who should receive an email regarding daily posting files?
ZRent (if licensed) Monthly reports should be sent to:
Technical Contact for file extract questions:
General FI Info |  |  | Logo & Branding
Routing Number: |  |  | Primary Color for Branding: |  | See below
Employer Identification Number (EIN) |  |  | Frame Color for Branding: |  | See below
Core Provider & Platform: |  |  | Font Color for Branding: |  | See below
Online Banking Provider (Consumer): |  |  | Online Banking Provider (Business):
ZRent (If Licensed)
ZRent Specific URL Redirect |  |  | ZRent Specific About Us
If you like, we can modify the URL where potential ZRent customers get directed to online account opening or to a specific webpage Please enter your URL in this box if you want this updated. Otherwise, we will use the FI home page URL. |  |  | Please enter the About Us message for your FI you'd like on your ZRent site. You can see an example at the bottom of the page: https://www.zrent.net/#partners
ZRent URL
Your ZRent URL will be bankdomain.zrent.net - we will build this and there is very little lift for you. The site will be published at ZEscrow go-live, but you will be able to review and approve.
Please send light & dark versions of logo in either .png or .svg

## Action - ZEscrow
ZSuite Partner Questionnaire
File Formatting, Processing, & Transfers
Outgoing Files to ZSuite Containing Customer Data*
*Please refer to https://zsuitetech.readme.io/docs/getting-started for format requirements.
File Naming Convention (CSV): | Must contain "organization" Must contain "balance" Must contain "signer" Must contain "transaction"
Incoming Files from ZSuite Containing Transaction Data
Posting File Type: | NACHA
File Naming Convention (dictated by FI/core provider): | ZESCROW-transactionYYYYMMDD
Generate daily posting file at 4pm local time. If you want a different time, add it here | 4:00 PM (Local time)
Interest General Ledger Number:
Do you want to receive the transaction file on National Holidays?
Transaction Codes and Descriptions (disregard if using NACHA files) – The data below will be included in the incoming files that ZSuite generates which contain the data for transactions initiated by your clients (non-interest debits and credits) as well as those that the platform calculates (interest debits and credits).
Test Accounts
ZSuite recommends the FI to create a test operating and test holding account. Test accounts may depend on the product type being created. These can be provided later as they may not be available on the FI core yet.
Operating Account Number:
Holding Account Number:

## Action - SSH Keys
As part of the prep work, we need a technical or IT person on your side to set up the SSH keys for both your staging and production sites. To configure your user, we need the public key of your ssh keypair. You can generate a private and public key pair using a utility like ssh-keygen: ssh-keygen -t rsa -b 4096 This will generate two files. The public key (.pub) needs to be sent to us and the private key should be configured with your sftp connection to our server so that we can authenticate you. Once we configure your user, we'll send you the username and hostname. We recommend you use a different set of keys for each environment (staging/testing and the production environment). To do this, you can perform this process twice.

## Action - ZE Goals
ZSuite Partner Questionnaire
Goals for ZEscrow
What goals do you have for ZEscrow at your FI?
Will your team have any incentives tied to ZEscrow deposit growth?
How will you measure success with the ZEscrow product?
ZSuite's most successful FIs have the sales team in the community to sell the ZEscrow product and perform their own demos. Does your FI prefer to handle the sales and demos or do you prefer to have the ZSuite Success team lead demos with your bankers and their clients?

## Interest Rates
ZSuite Partner Questionnaire
You only need to provide interest rates for the verticals you'll onboard Day 1
Default Sub-Account Interest Configurations
Interest Rate Segments | Default Interest Rates | Tax-Reporting Splits | Org Fee (deducted from interest)
SAMPLE 1 (Prop Management, CT) | 0.15% | 100% Beneficiary | None
SAMPLE 2 (Prop Management, NY) | 0.1% | 100% Beneficiary | 1%
SAMPLE 3 (Insurance Companies) | 0.75% | 50% Beneficiary, 50% Org | None
Property Management
Health Care
Title Company
Real Estate Office
Funeral Home
Attorney
IOLTA
Municipality
1031 Exchange
Non-Profit
HOA
Retirement and Assisted Living
Other (please specify):

## FI Users
*Please provide a list of FI Employees for the Staging Site and Production Site (add more rows if needed)
Will either FI Users or FI Customers log in via Single Sign On? | FI Users? | FI Customers SSO via Online Banking?
Staging Site (FI Testing)
First Name | Last Name | Email
Production Site (FI Employee Access) - if different from Staging
First Name | Last Name | Email

## Project Checklist
ZSuite Project Checklist
| Intros & Kickoff | Occurs in Project | Who? | Complete? | Notes
| Intro Call | Week 1 | ZSuite Sales
| Kickoff Call & Discovery call | Week 1 | ZS Implementation Lead
| Extract Review Call - if desired (highly recommended) | Week 1 or 2 | ZS Implementation Lead
Prep Work Tasks
| Safelist ZSuite domains | Week 2 | FI IT SME
| Identify if SSO is needed | Week 2 | FI IT SME
| Review T&Cs | Week 2 | FI Compliance SME
| Send Logo to ZSuite | Week 2 | FI Marketing SME
| Complete Implementation Questionnaire (most is completed during Discovery call) | Week 2 | FI Project Lead or Business Admin
| Create SSH Key for staging site | Week 3 | FI IT SME
| Create SSH Key for production site | Week 3 | FI IT SME
| FI to turn off visibility for holding account in OLB | Week 2 or 3 | FI
| FI to turn off statements for holding account | Week 2 or 3 | FI
| FI to turn off interest for holding account | Week 2 or 4 | FI
| Create Staging site | Week 4 | ZS Dev Team
| Create production site | Week 4 | ZS Dev Team
| Set up SFTP access using SSH Keys | Week 5 | ZS Dev Team
| IF NEEDED: Create ZRent site | Weeks 5-7 | ZS Dev Team
Core Extracts
| Create core extract files based on template provided | Week 2 | FI Data SME
| Milestone Call: File Review | Week 2 or 3
| Iterate & adjust extract files as needed | Week 3-5 | FI Data SME
Core Extract Validation
| Ensure daily files work as expected | Week 5-6 | FI Data & Business SME & ZSuite
| Test transaction & transaction file within staging site | Week 5-6 | FI Data & Business SME
New Business: Training & Marketing
| Add ZEscrow (and ZRent, if licensed) to Services/Tools page of FI website | Week 2 or 3 | FI Marketing/Web Team
| Discuss new product launch with FI Sales team & Support/Ops Teams | Week 4 | FI Project Lead + ZSuite Client Team
| Hold training webinars for Support/Ops Team | Week 5 | FI Project Lead + ZSuite Client Team |  | FI may want SOPs in place
| Ensure FI has new Escrow account opening documentation | Week 4-5 | FI
| Hold training webinars for Sales team as needed | Week 6-8 (depending on extract timing) | FI + ZS Client Team
| Issue press release | Week 8 | FI Marketing SME
Migrations
*Migrations = moving subaccounts from one platform to ZSuite
| MIGRATIONS: Send existing database of subaccount information | Week 3-4 | FI Data SME
| Migration Milestone Call: Interest Configs & Foldering for Existing Subs | Week 5 | FI Business SME & ZS Product team
| IF NEEDED: Migration dry run | Week 5-6 | ZSuite Dev Team
Migration/Existing Business: Training & Marketing
| Discuss marketing & rollout plan for existing customers | Week 7-8 | FI Marketing SME + ZSuite Client Team
| Hold webinars as needed | Week 8-9 | FI + ZS Client Team
Project Close
| Confirm all items are complete | Week 12 | ZS Implementation Lead
| Schedule regular Success touch points | Week 12 | ZS Client Team

## Testing Checklist
ZSuite Testing Checklist
| Test Steps | Who? | Complete? | Notes
| Test SSO (if applicable) | ZS Implementation Lead
| Open Test org (via alarm bell) | ZS/FI
| Open test subaccount(s) | FI
| Perform transaction in test subaccount (ensure holding or operating has funds) | FI
| Email ZSuite to confirm test transaction is done | FI
| Confirm FI receives daily transaction file at EOD | FI/ZS
| FI process test transaction on core | FI
| FI generates daily files and automatically sends to ZS next business morning | FI
| FI to turn off statements for holding account | FI
FI to ensure holding account does not close at $0 Balance
| FI to disable access to holding account on OLB | FI
| FI to turn off interest for holding account | FI
| Set up FI Admin Training | FI/ZS
Migrations
*Migrations = moving subaccounts from one platform to ZSuite
| Confirm via spot-check subaccounts are in the right org and folder | FI Data SME
| Confirm via spot-check subaccount interest configs are correct | FI Business SME & ZS Product team